## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Rohitha | 2026-07-05 | faiss module not found | Sprint 1 | Rohitha | Maintainability | Installed FAISS package | 2026-07-05 | Closed | Resolved
2 | Rohitha | 2026-07-20 | GitHub push rejected | Sprint 2 | Rohitha | Standards | Pulled latest changes and merged | 2026-07-20 | Closed | Fixed
3 | Rohitha | 2026-07-18 | JSON output formatting issue | Sprint 2 | Rohitha | Logical | Updated output formatting | 2026-07-18 | Closed | Verified
4 | Rohitha | 2026-07-16 | Indentation error in Python | Sprint 2 | Rohitha | Logical | Corrected indentation | 2026-07-16 | Closed | Tested

## Sheet2
Logical
User Interface
Maintainability
Standards
Others