## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Rohitha | 2026-07-05 | faiss module not found | Sprint 1 | Rohitha | Maintainability | Installed FAISS package | 2026-07-05 | Closed | Resolved
2 | Rohitha | 2026-07-20 | GitHub push rejected | Sprint 2 | Rohitha | Standards | Pulled latest changes and merged | 2026-07-20 | Closed | Fixed
3 | Rohitha | 2026-07-18 | JSON output formatting issue | Sprint 2 | Rohitha | Logical | Updated output formatting | 2026-07-18 | Closed | Verified
4 | Rohitha | 2026-07-16 | Indentation error in Python | Sprint 2 | Rohitha | Logical | Corrected indentation | 2026-07-16 | Closed | Tested
5 | Rohitha | 2026-07-25 | Root cause output required improvement | Sprint 3 | Rohitha | Logical | Improved root cause analysis prompt and output structure | 2026-07-25 | Closed | Verified
6 | Rohitha | 2026-07-27 | Duplicate detection similarity output issue | Sprint 3 | Rohitha | Logical | Updated similarity search and result handling | 2026-07-27 | Closed | Tested
7 | Rohitha | 2026-08-04 | Defect analytics output formatting issue | Sprint 4 | Rohitha | Logical | Updated analytics calculation and display | 2026-08-04 | Closed | Verified
8 | Rohitha | 2026-08-07 | Knowledge base growth validation issue | Sprint 4 | Rohitha | Logical | Tested resolved-bug addition and validation flow | 2026-08-07 | Closed | Tested

## Sheet2
Logical
User Interface
Maintainability
Standards
Others